## Feuil1
Id. | Problem description | Problem config number | Criticity | Solution type | Solution description | Solution config number
1 | Conformance to SCA 1.1 La spec SCA 1.1 (celle dont nous utilisons les schémas) n'autorise plus les valeurs directement en tant que fils de l'élément sca:property. Ce changement est du à la possibilité d'avoir plusieurs valeurs pour une property. Il faudra donc remplacer : <sca:property name="nb">"9"</sca:property> par <sca:property name="nb"><sca:value>"9"</sca:value></sca:property> Par ailleurs nous ne voyons pas l'intérêt de l'ajout de guillemets et proposons la forme : <sca:property name="nb"><sca:value>9</sca:value></sca:property> | 1.7.6 | NON_BLOCKING | ONGOING | The standard SCA XSD does not contain the whole specification of SCA 1.1. Two solutions: - Add additionnal verification within parsers - Add appropriate definitions within the SCA XSD A bug report can be sent to OASIS. | Iter. 2 | BLOCKING
2 | Dans le document de spécification, la façon de fixer les valeurs des property ne semble pas définie. Il y a bien des exemples, mais certains sont manquants (records), il faudrait une définition de chaque syntaxe dans le cas général pour chaque type. | 1.7.6 | RFE | ONGOING | Introduisons par exemple une balise « field » sous « sca:property ». Exemple : <sca:property name="nb"> <field name =”x”> <sca:value>9</sca:value> </field> <field name =”y”> <sca:value>10</sca:value> </field> <field name =”str”> <sca:value>”ceci est un chaine”</sca:value> </field> </sca:property> | Iter. 2 | NON_BLOCKING
3 | Ne peut on pas imaginer le trigger comme un sender particulier ? Le modèle comporterait alors la définition d'un eventlink avec un fils trigger et/ou plusieurs opérations. | 1.7.6 | RFE | REJECTED | Pas d’accord : un trigger instance n’est pas un module, mais une ressource plate-forme. Gardons la notation actuelle car le trigger instance ne fourni pas non plus d’opération eventSent. Do we need a powerful trigger concept ? In order to synchronize finely two modules on the same clock top. Seem to be overspecifying. The real need is to synchronize at events at the source => this is already the case. the IAS specifies multi-frequency triggers | N/A | RFE
4 | Par ailleurs ne serait-ce pas mieux de fixer la période du trigger dans le triggerInstance plutôt que dans l'eventLink ? La périodicité est attachée au trigger est non au lien. | 1.7.6 | RFE | ONGOING | On pourrait imaginer avoir besoin des deux : - Une période sur le trigger instance - Une période (compatible, sous-fréquence harmonique) sur l’eventLink | Iter. 2
5 | Le schéma sca-core importe sca-policy mais ce dernier a été entièrement commenté. L'import et le fichier sca-policy devraient donc être supprimés. | 1.7.6 | NON_BLOCKING | FIX | If, in the future, it will be required, it will be added accordingly to the need. | 1.7.10 | WORKAROUND
6 | Certaines "références" ont gardé leur extension de fichiers comme : <ecos-sca:instance componentType="C1.componentType"> Dans la section qui décrit les conventions de nommages des spécifications ECOS draft P, il est dit que les componentType ont pour unique extension ".componentType". Il serait donc préférable de supporter la définition ou non de cette extension. | 1.7.6 | NON_BLOCKING | ONGOING | Remove all extensions in example | 1.7.10 | FIX
7 | Voire d'y ajouter une version : <ecos-sca:instance componentType="C1" version="1.0"> ou <ecos-sca:instance componentType="C1-1.0"> | 1.7.6 | RFE | ONGOING | To be discussed further Intermediate fix within 1.8.0 | Iter. 2 | ONGOING
8 | Problem with colon in the example (service definition) | 1.7.6 | BLOCKING | FIX | Separate the example from the model | 1.7.10 | REJECTED
9 | Introduce new QoS attributes (min, maxTimeInterval) | 1.7.6 | NON_BLOCKING | FIX | Associated to new XSD related to QoS | 1.8.0
10 | Add version number to the OS type within the logical platform | 1.7.10 | NON_BLOCKING | FIX |  | 1.8.0
11 | Add isSupervisionModule at module instance level | 1.7.10 | BLOCKING | FIX | missing for lifecycle tests - TBC | 1.8.0
12 | sca-contribution not validated with current model | 1.8.0 | NON_BLOCKING | ONGOING
14 | Link in logical system too complex? | 1.8.2-beta | NON_BLOCKING | ONGOING
15 | ecos-sca:implementation path replaced by the logical name | 1.8.2-beta | NON_BLOCKING | FIX |  | 1.8.2-gamma
17 | “extends” on records usefull? | 1.8.2-beta | NON_BLOCKING | FIX | Provides an 'extends' attributes to enable records inheritance for the languages that support it. Removed, waiting for language binding clarification. | 1.8.2-delta
18 | Fifosize too small | 1.8.2-beta | NON_BLOCKING | FIX | Fifosize sets to 8. | 1.8.2-gamma
19 | "maxVersion" on dataLink instead of dataRead dataWritten | 1.8.2-beta | NON_BLOCKING | REJECTED | To be discussed further. The current specification already enables to define heterogeneous maxVersion attributes.
20 | Multiplatesformes | 1.8.2-beta | BLOCKING | FIX | A new level logicalComputingPlatform" has been added to the logical system and a deployment can be done on this new level. | 1.8.2-gamma
21 | Engineer notation for time values with conversion to integer for API | 1.8.2-beta | NON_BLOCKING | FIX | Proposal to use engineer notation (i.e. 230e-3) and to apply a float to integer conversion in the API with nanosecond precision. | 1.8.2-delta
22 | A moduleInstance can reference moduleImplementation that does not exist | 1.8.2-beta | NON_BLOCKING | FIX | Bull patch applyied | 1.8.2-gamma
23 | Referencing an instance name of dynamic trigger that does not exist | 1.8.2-beta | NON_BLOCKING | FIX | Bull patch applyied | 1.8.2-gamma
24 | Add a optional comment field on types and operations | 1.8.2-beta | NON_BLOCKING | FIX | A comment field is added for each operationa and type. | 1.8.2-gamma
25 | Datalink readers cannot specify fifosize of activating datas | 1.8.2-gamma | BLOCKING | FIX | Datalink readers could be OpRefActivatingFifo | 1.8.2-delta
26 | Datalink writers can specifty an useless activating attribute | 1.8.2-gamma | NON_BLOCKING | FIX | Datalink writers could be OpRef | 1.8.2-delta
27 | No compatibility between 1.8.2-beta and 1.8.2-gamma for deployment files | 1.8.2-gamma | NON_BLOCKING | FIX | computingPlatform attribute is now optional | 1.8.2-delta
28
29
30
31
32
33
34